## Roadmap
|  |  | Milestone 1: Prep |  | Milestone 2: CRP1 |  | Milestone 3 |  | Milestone 4 |  | Milestone 5 |  | Milestone 6
|  |  | Date: March 31, 2024 |  | Date: ? |  | Date: ? |  | Date: ? |  | Date: ? |  | Date: ?
Methodology | Project | Discover |  | Design |  | Develop |  | Test |  | Train |  | Rollout
Waterfall | Functional Architecture | Requirements/Scope documentation
| Technical Architecture | Architecture, Dev Tools
| Major Development and Integrations | Understand major gaps; internal, external, and Dual Write integrations
|  | Iteration 1 |  | Iteration 2 |  | Iteration 3 |  | Final Iteration |  | UAT |  | Training
Iterative | Process Design, Configuration, Testing | Configure and test initial environments
| Minor Development and Integrations | Document list of minor gaps
Security
|  | Initial List |  | Prioritized List |  | Prioritized List |  | Prioritized List |  | Prioritized List |  | Rollout
Agile | Data Migration | Review existing capabilities, setup infrastructure
| Data Warehouse and Reporting | Review existing reports and source systems, setup Power BI
Documentation, End User Training, and Rollout
|  | Picard |  | La Forge |  | Data |  | Worf |  | Troi |  | Riker
Just-In-Time | Business Processes Reengineering and Change Management | Client list of processes they'd like to change during the implementation
| Environments, Cloud, Hardware, Device Procurement, Licensing | D365 environemnts, get really big monitors for project team.
©2024 Joel Leichty ¦ MIT License
The MIT License – Open Source Initiative